## Read Me
Midwest Precision Parts — Remediation Roadmap
Prioritized Action Plan & Mitigation Strategy ¦ Portfolio Project
Scenario
Midwest Precision Parts is a fictional small manufacturer that makes custom metal components for commercial customers. The company has about 85 employees and runs on a mix of office systems, production workstations, shared file storage, email, vendor portals, and a handful of cloud applications. The company has grown fast, but nobody's ever sat down and formally reviewed its security program. Leadership is starting to worry about the obvious stuff — ransomware, production downtime, people having access they shouldn't, documentation that doesn't really exist, and whether they could actually recover if something went wrong.
Objective
I evaluated the company's current cybersecurity practices against the NIST Cybersecurity Framework to find the gaps that actually matter to the business, not just the ones that look bad on paper. The goal was to turn a framework review into something leadership could read, understand, and act on — not a 40-page report that gets filed away and forgotten.
Scope
This assessment covers: • Identity and access management • Asset inventory • Data protection • Endpoint security • Email and phishing defenses • Backup and recovery • Incident response readiness • Vendor and third-party risk • Security awareness training • Policies and procedures Operational technology, industrial control systems, and physical plant equipment were out of scope.
Assumptions
• Findings are based on the fictional environment and stakeholder representations described above, not on technical testing. • No vulnerability scanning or penetration testing was performed as part of this scenario. • Current state reflects a single point in time and assumes no changes were made during the engagement.
Methodology
1. Review the business environment and assumptions 2. Compare current practices against NIST CSF categories 3. Identify gaps across governance, protection, detection, response, and recovery 4. Rate each gap by business impact and urgency 5. Recommend remediation steps that are realistic for a company this size 6. Organize the recommendations into a phased roadmap
Key Risk Themes
• Limited asset inventory • Inconsistent user access reviews • Backup processes that aren't regularly tested • No formal incident response plan • Limited phishing and security awareness training • No documented vendor risk review process • No clear ownership of cybersecurity responsibilities
Disclaimer
Midwest Precision Parts is a fictional company created for portfolio purposes. All findings, risks, and recommendations in this workbook are fictional and don't represent any real company or client.

## Lookup
Phase | Status
Phase 1 (0-30) | Not Started
Phase 2 (31-90) | Blocked
Phase 3 (91-180) | Completed
Phase 4 (180+)

## Remediation Roadmap
Action ID | Phase | Target Window | Related Gaps | Risk Theme | Recommended Action | Dependencies | Assigned Owner | Est. Effort | Status | Success Metric | Risk Reduction Score
RM-01 | Phase 1 (0-30) | 0-30 Days | GAP-01 | Cyber Ownership | Formally designate a cybersecurity lead with executive sponsorship. | None | Leadership | Low | Not Started | Ownership charter signed. | 4
RM-02 | Phase 1 (0-30) | 0-30 Days | GAP-06 | Access Management | Enforce Multi-Factor Authentication (MFA) across all M365 and VPN portals. | None | IT | Low | Not Started | 100% MFA enrollment. | 5
RM-03 | Phase 1 (0-30) | 0-30 Days | GAP-10 | Backup & Recovery | Execute a full sandboxed test restore from current backup media. | None | IT | Medium | Not Started | Restore test successful & logged. | 5
RM-04 | Phase 1 (0-30) | 0-30 Days | GAP-13 | Incident Response | Draft and distribute an initial one-page Incident Response contact sheet. | RM-01 | Ops | Low | Not Started | Contact sheet distributed. | 4
RM-05 | Phase 2 (31-90) | 31-90 Days | GAP-04, GAP-05 | Asset Management | Deploy an automated asset discovery tool to log hardware/software. | None | IT | Medium | Not Started | Central inventory populated. | 5
RM-06 | Phase 2 (31-90) | 31-90 Days | GAP-07 | Access Management | Initiate the first quarterly access review for all critical systems. | RM-05 | HR/IT | Medium | Not Started | Access review completed. | 4
RM-07 | Phase 2 (31-90) | 31-90 Days | GAP-08 | Security Training | Procure and launch a managed security awareness and phishing platform. | None | HR | Low | Not Started | 100% staff onboarding. | 4
RM-08 | Phase 2 (31-90) | 31-90 Days | GAP-09 | Data Protection | Configure MDM to enforce BitLocker encryption on all corporate laptops. | None | IT | Low | Not Started | 100% devices encrypted. | 3
RM-09 | Phase 3 (91-180) | 91-180 Days | GAP-11 | Endpoint Security | Roll out a centrally managed Endpoint Detection and Response (EDR) agent. | RM-05 | IT | High | Not Started | EDR deployed on all hosts. | 5
RM-10 | Phase 3 (91-180) | 91-180 Days | GAP-02 | Vendor Risk | Implement a mandatory security questionnaire for new vendor onboarding. | None | Finance | Medium | Not Started | Process integrated into AP. | 3
RM-11 | Phase 3 (91-180) | 91-180 Days | GAP-03 | Policy | Draft, approve, and distribute Acceptable Use and core security policies. | RM-01 | HR | Medium | Not Started | Policies signed by all staff. | 3
RM-12 | Phase 4 (180+) | 180+ Days | GAP-12 | Continuous Monitoring | Stand up a centralized log aggregator (syslog) for network/server telemetry. | None | IT | High | Not Started | Logs centralized for 30 days. | 3
RM-13 | Phase 4 (180+) | 180+ Days | GAP-14 | Recovery Planning | Build out comprehensive Disaster Recovery playbooks for core systems. | RM-03 | IT/Ops | Medium | Not Started | DR playbooks documented. | 3